## ICT
Portfolio Dutch Federal IT 2007
mln eur
| Expected failing IT millions (mln EUR): | 2362.495 |  | normal risk | 17.88% | 1040.4198 |  |  | C3 = sum(cost * p) * 75%
| Expected probability of failure | 40.45% |  | risk excess | 22.57% | 1318.3392 |  |  | C4 = C3 / sum(cost) | [13 empty] | Nr. Ministerie Project
referred table(T1):
| %Largest project of IT component: | 100 | [20 empty] | https://www.tweedekamer.nl/downloads/document?id=2009D34255
| %Failed of project in case that software failes: | 100 | [17 empty] | empty = no source |  | T=time
[14 empty] | from this column on is data collected by our own | [7 empty] | M=Cost
Min | Description | Planned Cost (mln EUR) | % IT | time period | Planned Duration (year) | IT EUR(mln) | IT/year | software EUR(mln) | dollars 99 | Benchmark | size (FP) | probability of failure | failure(mln EUR) |  | Current status | Combined status | Online date | Actual Duration (year) | Time Overrun (years) | Lastest cost | Cost Overrun (mln EUR) | Overrun(M&T) | info link
BZK | P-direkt | 700 | 42 | 2004-2018 | 12 | 294 | 24.5 | 294 | 265950956.1 | MIS | 46092.1361 | 47.27% | 330.8619 |  | active | completed | 31-12-2010 | 4 | -8 | 115.91 | -584.09 |  | https://rijksictdashboard.nl/ict-activiteiten/e404d751-2023-4ddb-86c1-5469bc63317f
VenW | BB (Beter Benutten) 21 | 300 | 75 | 1999-2008 | 9 | 225 | 25 | 225 | 203533895 | MIS | 38347.47 | 46.85% | 140.559 |  | active | completed | [6 empty] | https://www.treinreiziger.nl/prorail-tot-2030-extra-veel-spoor-vernieuwen-ook-overdag-en-buiten-vakanties/
FIN | Aanslagbelastingensysteem (ABS) | 226 | 99 | 1999-2008 | 9 | 223.74 | 24.86 | 223.74 | 202394105.2 | MIS | 38199.6532 | 46.84% | 105.865 |  | active | completed | [6 empty] | https://zoek.officielebekendmakingen.nl/kst-31066-992.html
FIN | Toeslagen | 275 | 81 | 2005-2008 | 3 | 222.75 | 74.25 | 222.75 | 201498556.1 | MIS | 38083.329 | 46.83% | 128.796 |  | active | completed | 23-12-2011 | 6 | 3 | 240 | -35 | T | https://rijksictdashboard.nl/ict-activiteiten/e65803ab-6288-40f4-95bb-7b4ba269a327
FIN | Complexiteitsreductie | 200 | 90 | 2006-2015 | 9 | 180 | 20 | 180 | 162827116 | MIS | 32891.8814 | 46.4% | 92.8061 |  | suspended | suspended | [6 empty] | T1
SZW | Vernieuwing (UWV) | 260 | 62 | 2007-2011 | 4 | 161.2 | 40.3 | 161.2 | 145820728.3 | MIS | 30488.8662 | 46.14% | 119.9683 |  | active | completed | [6 empty] | https://www.uwv.nl/nl/over-uwv
FIN | Samenwerking UWV-Belastingdienst (SUB) | 165 | 94 | 2003-2008 | 5 | 155.1 | 31.02 | 155.1 | 140302698.3 | MIS | 29690.6397 | 46.04% | 75.9724 |  | active | completed | [6 empty] | https://www.loonaangifteketen.nl/binaries/loonaangifteketen/documenten/convenanten/2020/03/09/convenant-samenwerking-loonaangifteketen-belastingdienst-uwv-cbs/Convenant+samenwerking+loonaangifteketen+Belastingdienst+UWV+CBS.pdf
VenW | VTI, Programma Vaste Telecom Infra | 117 | 100 | 2006-2011 | 5 | 117 | 23.4 | 117 | 105837625.4 | MIS | 24458.1424 | 45.22% | 52.9132 |  | cancelled | cancelled | [6 empty] | T1
VenW | InfoPlus | 143 | 80 | Oct 2000 - Oct 2009 | 9 | 114.4 | 12.7111 | 114.4 | 103485678.2 | MIS | 24083.0412 | 45.15% | 64.5667 |  | cancelled | cancelled | [6 empty] | T1
JUS | Project Invoering Protocol Identiteitsvaststelling | 100 | 90 | -2010 | 5.7004 | 90 | 15.7883 | 90 | 81413558 | MIS | 20420.2529 | 44.29% | 44.2924 |  | active | completed | [6 empty] | https://www.strafrechtketen.nl/actueel/nieuws/2021/11/22/protocol-identiteitsvaststelling
FIN | Herinrichting invorderingsproces(renamed to ETM) | 78 | 100 | 2005-2008 | 3 | 78 | 26 | 78 | 70558416.94 | MIS | 18506.3208 | 43.71% | 34.0967 |  | active | completed | 31-12-2010 | 5 | 2 | 175.3 | 97.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/44407368-191b-4ae7-b727-7eab039661b7
DEF | MULAN | 77.3 | 100 | 2003-2007 | 4 | 77.3 | 19.325 | 77.3 | 69925200.37 | MIS | 18391.9402 | 43.68% | 33.7612 |  | active | completed | [6 empty] | https://zoek.officielebekendmakingen.nl/kst-36100-X-1.html
SZW | wet Werk en Inkomen naar Arbeidsvermogen (UWV) | 127 | 60 | Oct 2005 till medio 2008 | 2.8 | 76.2 | 27.2143 | 76.2 | 68930145.78 | MIS | 18211.5432 | 43.61% | 55.3905 |  | cancelled | cancelled | [6 empty] | T1
BZK | Reisdocumentenprogramma | 84.5 | 90 | 2005-2009 | 4 | 76.05 | 19.0125 | 76.05 | 68794456.51 | MIS | 18186.8809 | 43.61% | 36.8472 |  | unknown | unknown
JUS | Implementatie C2000 | 72.5 | 100 | 2006-2009 | 3 | 72.5 | 24.1667 | 72.5 | 65583143.95 | MIS | 17598.6801 | 43.4% | 31.4643 |  | active | completed | [6 empty] | https://www.adviescollegeicttoetsing.nl/documenten/publicaties/2016/11/22/bit-advies-implementatie-vernieuwing-c2000
LNV | Elektronische Dienstverlening LNV (EDV) | 94.5 | 75 | 2003-2011 | 8 | 70.875 | 8.8594 | 70.875 | 64113176.93 | MIS | 17326.4437 | 43.3% | 40.9174 |  | unknown | unknown
VWS | Diagnose Behandeling Combinaties (DBC) in de curatieve zorg | 162 | 35 | 2000-2007 | 7 | 56.7 | 8.1 | 56.7 | 51290541.54 | MIS | 14861.4584 | 42.25% | 68.4441 |  | active | completed | [6 empty] | https://www.zorgcijfersdatabank.nl/toelichting/rapport-2022/medisch-specialistische-zorg
JUS | Vernieuwing informatievoorziening DJI | 50 | 100 | 2002-2012 | 10 | 50 | 5 | 50 | 45229754.45 | MIS | 13630.2039 | 41.61% | 20.8044 |  | active | completed | 31-12-2013 | 11 | 1 | 4.2 | -45.8 | T | https://rijksictdashboard.nl/ict-activiteiten/7322396e-dea8-4d38-9273-c197eb79180c
VenW | Modernisering Objecten Bediening Zeeland | 62 | 80 | 2004-2010 | 6 | 49.6 | 8.2667 | 49.6 | 44867916.41 | MIS | 13555.1186 | 41.57% | 25.7713 |  | active | completed | 31-12-2018 | 14 | 8 | 62.93 | 0.93 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f50705ba-ec4e-4893-ac46-ff5ed127e922
DEF | SPEER | 150 | 33 | till 2013 | 4.7897 | 49.5 | 10.3348 | 49.5 | 44777456.9 | MIS | 13536.3178 | 41.56% | 62.3341 |  | active | completed | 31-12-2015 | 6.7897 | 2 | 276.44 | 126.44 | M&T | https://rijksictdashboard.nl/ict-activiteiten/85e1279b-0c14-45f1-b144-3144cf75c544
SZW | Walvis/SUB SZW Digitaal Klantdossier (CWI) | 59.1 | 80 | 2005-2008 | 3 | 47.28 | 15.76 | 47.28 | 42769255.8 | MIS | 13115.8254 | 41.31% | 24.4159 |  | cancelled | cancelled | [6 empty] | T1
VWS | Implementatie EMD/WDH | 56.8 | 80 | 2005-2009 | 4 | 45.44 | 11.36 | 45.44 | 41104800.84 | MIS | 12762.6169 | 41.1% | 23.3442 |  | unknown | unknown
FIN | Basisregistraties | 46 | 93 | 2007-2010 | 3 | 42.78 | 14.26 | 42.78 | 38698577.9 | MIS | 12243.9875 | 40.77% | 18.7531 |  | active | completed | 31-12-2015 | 8 | 5 | 42.7 | -3.3 | T | https://rijksictdashboard.nl/ict-activiteiten/2de4f98a-9342-40b8-b5c4-c76d6269cc92
BZ | Werken in de Toekomst (WIT) | 50 | 85 | 2008-2001 | 7 | 42.5 | 6.0714 | 42.5 | 38445291.28 | MIS | 12188.8175 | 40.73% | 20.3655 |  | cancelled | cancelled |  |  |  | 10 | -40 |  | T1
JUS | Vernieuwing IND (renamed to INDIGO) | 80 | 50 | 2006-2010 | 4 | 40 | 10 | 40 | 36183803.56 | MIS | 11691.0724 | 40.39% | 32.312 |  | active | completed | 31-12-2013 | 7 | 3 | 98 | 18 | M&T | https://rijksictdashboard.nl/ict-activiteiten/7bec8d3e-7062-41fb-a2e3-bdc1edf7c518
OCW | Wijziging studiefinancieringssytemen IBGroep | 54.2 | 72 | 2006-2011 | 5 | 39.024 | 7.8048 | 39.024 | 35300918.75 | MIS | 11494.1334 | 40.25% | 21.815 |  | cancelled | cancelled | [6 empty] | T1
JUS | Programma NoorderWint | 35 | 95 | 2005-2010 | 5 | 33.25 | 6.65 | 33.25 | 30077786.71 | MIS | 10295.5924 | 39.31% | 13.7577 |  | active | completed | 31-01-2011 | 6 | 1 | 55 | 20 | M&T | https://rijksictdashboard.nl/ict-activiteiten/6a20e4b6-c125-48c5-b5c7-3fa1f7356ea6
SZW | USMF (UWV) | 31.1 | 100 | 2002-2007 | 5 | 31.1 | 6.22 | 31.1 | 28132907.27 | MIS | 9832.9911 | 38.9% | 12.0984 |  | cancelled | cancelled | [6 empty] | T1
DEF | PALS | 36.6 | 82 | 2006-2011 | 5 | 30.012 | 6.0024 | 30.012 | 27148707.81 | MIS | 9595.1017 | 38.68% | 14.1577 |  | active | completed | 31-12-2015 | 9 | 4 | 29 | -7.6 | T | https://rijksictdashboard.nl/ict-activiteiten/2e6d6fb1-50c7-47bc-8d56-d5e0fe5d95d1
OCW | Invoering van het persoonsgebonden nummer (PGN, ook wel onderwijsnummer) in het Primair Onderwijs | 60 | 50 | 2005-2009 | 4 | 30 | 7.5 | 30 | 27137852.67 | MIS | 9592.463 | 38.68% | 23.2079 |  | unknown | unknown
FIN | Sagitta binnenbrengen | 33.5 | 87 | 2006-2007 | 1 | 29.145 | 29.145 | 29.145 | 26364423.87 | MIS | 9403.6004 | 38.5% | 12.8976 |  | unknown | unknown
VenW | Herman | 30.5 | 95 | Q3-2006 t/m Q1-2009 | 2.5 | 28.975 | 11.59 | 28.975 | 26210642.7 | MIS | 9365.8437 | 38.46% | 11.7314 |  | cancelled | cancelled | [6 empty] | T1
SZW | SVB Tien (SVB) | 92 | 30 | 2006-2010 | 4 | 27.6 | 6.9 | 27.6 | 24966824.45 | MIS | 9057.8663 | 38.16% | 35.1057 |  | cancelled | cancelled | 2014-02-09 | 8 | 4 | 121.8 | 29.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/09b1ce9a-294f-48db-96b9-bf5cb79305cc
JUS | ReIS | 45 | 60 | 2003-2010 | 7 | 27 | 3.8571 | 27 | 24424067.4 | MIS | 8921.9811 | 38.02% | 17.1086 |  | completed | completed | [6 empty] | T1
FIN | eCustoms | 47.6 | 55 | 2005-2012 | 7 | 26.18 | 3.74 | 26.18 | 23682299.43 | MIS | 8734.7353 | 37.82% | 18.0036 |  | active | completed | 31-12-2010 | 5 | -2 | 65.28 | 17.68 | M | https://rijksictdashboard.nl/ict-activiteiten/ce9d570c-f711-4bb1-953b-01a62f444c03
DEF | DIV-online | 57.7 | 45 | 2005-2012 | 7 | 25.965 | 3.7093 | 25.965 | 23487811.48 | MIS | 8685.3389 | 37.77% | 21.7932 |  | unknown | unknown
VenW | VenW Beschikbaarheid In Zicht (BIZ) 25 100 | 25 | 100 | NA | 2.5 | 25 | 10 | 25 | 22614877.22 | MIS | 8462.0337 | 37.53% | 9.3816 |  | cancelled | cancelled | [6 empty] | T1
FIN | Vooringevulde aangifte (VIA) | 45 | 55 | 2006-2008 | 2 | 24.75 | 12.375 | 24.75 | 22388728.45 | MIS | 8403.7464 | 37.46% | 16.8576 |  | active | completed | 2012-05-01 | 6 | 4 | 53.26 | 8.26 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f5a8b162-363e-480a-8d0f-e21c0eedae65
BZK | Modernisering Gemeentelijke Basisadministratie persoonsgegevens ( mGBA) | 35.3 | 70 | 2006-2009 | 3 | 24.71 | 8.2367 | 24.71 | 22352544.65 | MIS | 8394.4035 | 37.45% | 13.2202 |  | active | completed | [6 empty] | https://www.parlementairemonitor.nl/9353000/1/j9vvij5epmj1ey0/vm7yr0tfxszn
BZK | Rijksweb | 23 | 100 | 2005-2007 | 2 | 23 | 11.5 | 23 | 20805687.05 | MIS | 7990.4369 | 36.98% | 8.5062 |  | unknown | unknown
JUS | GPS | 90 | 25 | 2000-2010 | 10 | 22.5 | 2.25 | 22.5 | 20353389.5 | MIS | 7870.5651 | 36.84% | 33.1548 |  | active | completed | 31-12-2011 | 11 | 1 | 99.4 | 9.4 | M&T | https://rijksictdashboard.nl/ict-activiteiten/132afe97-ad4f-49fc-b789-f3010c85c893
OCW | Servicegericht bekostigen | 28.9 | 75 | 2004-feb 2007 | 3.2 | 21.675 | 6.7734 | 21.675 | 19607098.55 | MIS | 7670.9398 | 36.59% | 10.575 |  | completed | completed | [6 empty] | T1
VenW | VIP21 | 21.4 | 100 | 2005-2008 | 3 | 21.4 | 7.1333 | 21.4 | 19358334.9 | MIS | 7603.8734 | 36.51% | 7.8124 |  | cancelled | cancelled | [6 empty] | T1
VenW | Walradar Noordzeekanaal | 26.2 | 80 | 2005-2009 | 4 | 20.96 | 5.24 | 20.96 | 18960313.06 | MIS | 7496.0044 | 36.37% | 9.5285 |  | cancelled | cancelled | [6 empty] | T1
BZ | NVIS (Nieuw Visum Informatie Systeem) | 24.3 | 85 | 2005-2008 | 3 | 20.655 | 6.885 | 20.655 | 18684411.56 | MIS | 7420.8163 | 36.27% | 8.8137 |  | completed | completed | [6 empty] | T1
JUS | Managementinformatie & Datawarehousing DJI (MI&D) | 20 | 100 | 2005-2009 | 4 | 20 | 5 | 20 | 18091901.78 | MIS | 7258.1636 | 36.05% | 7.2108 |  | completed | completed | [6 empty] | T1
VWS | Programma Stroomlijning indicatieprocessen in Zorg en Sociale Zekerheid(renamed to Programma Stroomlijning Indicatieprocessen (STIP)) | 25 | 80 | 2006-2011 | 5 | 20 | 4 | 20 | 18091901.78 | MIS | 7258.1636 | 36.05% | 9.0135 |  | completed | completed | 2009-01-09 | 3 | -2 | 4.72 | -20.28 |  | https://rijksictdashboard.nl/ict-activiteiten/baa114a3-4559-407f-ba15-c4a30c800442
EZ | Bedrijvenloket | 20.9 | 90 | 2005-2010 | 5 | 18.81 | 3.762 | 18.81 | 17015433.62 | MIS | 6958.3261 | 35.64% | 7.4487 |  | unknown | unknown
JUS | Biometrie DJI | 18 | 100 | Oct 2006 - Q3 2008 | 2 | 18 | 9 | 18 | 16282711.6 | MIS | 6750.8416 | 35.34% | 6.3612 |  | unknown | unknown
BZK | Nationaal Schengen Informatiesysteem (NSIS-II)(renamed to NL-SIS-II (Nederlands Schengen Informatiesysteem)) | 17.5 | 100 | 2005-2008 | 3 | 17.5 | 5.8333 | 17.5 | 15830414.06 | MIS | 6621.3097 | 35.15% | 6.1508 |  | active | completed | 31-12-2013 | 8 | 5 | 22.8 | 5.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/1c2220dc-caea-45a3-8004-bfc173e3947f
VROM | Basisregistraties Adressen en Gebouwen(2.0) | 42 | 37.5 | till end 2009 | 3.4315 | 15.75 | 4.5898 | 15.75 | 14247372.65 | MIS | 6158.5017 | 34.42% | 14.4566 |  | active | completed | [6 empty] | https://www.geobasisregistraties.nl/basisregistraties/adressen-en-gebouwen/bag-wet-en-regelgeving
BZK | Basisvoorziening Handhaving (BVH) | 15 | 100 | Mar 2007 - Sep 2009 | 2.6 | 15 | 5.7692 | 15 | 13568926.33 | MIS | 5955.2848 | 34.08% | 5.1122 |  | cancelled | cancelled | [6 empty] | T1
BZK | HAVANK | 30 | 50 | t/m 2009 | 3.3831 | 15 | 4.4338 | 15 | 13568926.33 | MIS | 5955.2848 | 34.08% | 10.2243 |  | cancelled | cancelled | [6 empty] | T1
JUS | Implementatie Wet OM-afdoening | 16 | 90 | 2005-2009 | 4 | 14.4 | 3.6 | 14.4 | 13026169.28 | MIS | 5790.418 | 33.8% | 5.4074 |  | active | completed | [6 empty] | https://www.om.nl/onderwerpen/beleidsregels/aanwijzingen/executie/aanwijzing-om-strafbeschikking-2022a003#:~:text=Door%20de%20invoering%20van%20de,257a%20Sv).
VenW | ASTRIS | 20.5 | 70 | 2007-2011 | 4 | 14.35 | 3.5875 | 14.35 | 12980939.53 | MIS | 5776.5832 | 33.77% | 6.9232 |  | cancelled | cancelled | [6 empty] | T1
VenW | Trots | 18.7 | 70 | 2004-2009 | 5 | 13.09 | 2.618 | 13.09 | 11841149.71 | MIS | 5422.782 | 33.13% | 6.1945 |  | cancelled | cancelled | [6 empty] | T1
SZW | Digitaal Verzekeringsbericht (UWV) | 20.6 | 60 | Sept 2006 - Q1 2009 | 2.5 | 12.36 | 4.944 | 12.36 | 11180795.3 | MIS | 5212.9443 | 32.72% | 6.7404 |  | cancelled | cancelled | [6 empty] | T1
VenW | DONNA | 20 | 60 | till medio 2009 | 3.1703 | 12 | 3.7851 | 12 | 10855141.07 | MIS | 5108.0429 | 32.51% | 6.5022 |  | cancelled | cancelled | [6 empty] | T1
LNV | Relatie-identificatie LNV (Rel-id) | 25 | 45 | 2007-2009 | 2 | 11.25 | 5.625 | 11.25 | 10176694.75 | MIS | 4886.2796 | 32.05% | 8.0133 |  | unknown | unknown
SZW | Killen en Migreren (UWV) | 11 | 100 | 2006-2009 | 3 | 11 | 3.6667 | 11 | 9950545.978 | MIS | 4811.3414 | 31.89% | 3.5083 |  | active | completed | 31-12-2011 | 5 | 2 | 111 | 100 | M&T | https://rijksictdashboard.nl/ict-activiteiten/715d29e9-380c-430a-92b5-ef9848b7fde9
BZK | Basisvoorziening Opsporing (BVO) | 12 | 85 | Jan 2007 - medio 2008 | 1.5 | 10.2 | 6.8 | 10.2 | 9226869.907 | MIS | 4567.8702 | 31.36% | 3.7627 |  | cancelled | cancelled | [6 empty] | T1
EZ | Nieuw handelsregister | 20 | 50 | 2002-2010 | 8 | 10 | 1.25 | 10 | 9045950.889 | MIS | 4506.0826 | 31.21% | 6.2429 |  | cancelled | cancelled | [6 empty] | T1
BZK | Basisvoorziening Capaciteitsmanagement (BVCM) | 19 | 51 | Mar 2007 - Jul 2009 | 2.5 | 9.69 | 3.876 | 9.69 | 8765526.412 | MIS | 4409.5431 | 30.99% | 5.888 |  | cancelled | cancelled | [6 empty] | T1
DEF | Vervanging deelsystemen TITAAN | 200 | 100 | 2007-2021 | 14 | 200 | 14.2857 | 200 | 180919017.8 | Military | 21560.3333 | 28.33% | 56.6699 |  | unknown | unknown
DEF | TITAAN (Theatre Independent Tactical Army and Airforce Network) | 158.5 | 100 | 2001-2009 | 8 | 158.5 | 19.8125 | 158.5 | 143378321.6 | Military | 18404.9129 | 27.55% | 43.672 |  | active | completed | [6 empty] | https://www.computable.nl/2020/11/04/weg-vrij-voor-nieuwe-it-infrastructuur-defensie/
DEF | Herinrichting Personele Functiegebied | 36.1 | 22 | 2004-2009 | 5 | 7.942 | 1.5884 | 7.942 | 7184294.196 | MIS | 3845.7217 | 29.57% | 10.6745 |  | active | completed | 31-12-2011 | 7 | 2 | 37.9 | 1.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/c109adb4-3a3a-4df4-ba0f-5849ccc8a43d
DEF | F-16 Link-16 | 120.6 | 80 | 2000-2011 | 11 | 96.48 | 8.7709 | 96.48 | 87275334.18 | Military | 13129.3512 | 25.76% | 31.0683 |  | active | completed | [6 empty] | https://magazines.defensie.nl/defensiekrant/2016/22/dkdatalink
DEF | NIMCIS (Nieuw Mariniers Communicatie en Informatie Systeem) | 97.1 | 95 | 2002-2008 | 6 | 92.245 | 15.3742 | 92.245 | 83444373.98 | Military | 12734.4173 | 25.59% | 24.8504 |  | active | completed | [6 empty] | https://magazines.defensie.nl/materieelgezien/2022/02/nimcis-biedt-verbeterde-verbindingen-korps-mariniers
JenG | Elektronisch Kinddossier in de Jeugdgezondheidszorg | 14.27 | 35 | 2006-2009 | 3 | 4.9945 | 1.6648 | 4.9945 | 4518000.172 | MIS | 2795.3927 | 26.29% | 3.7518 |  | unknown | unknown
DEF | MILSATCOM lange termijn defensiebreed (Militaire Satelliet Communicatie) | 132 | 50 | 2001-2012 | 11 | 66 | 6 | 66 | 59703275.87 | Military | 10140.2463 | 24.31% | 32.0837 |  | active | completed | [6 empty] | https://www.rijksfinancien.nl/memorie-van-toelichting/2023/OWB/K/onderdeel/1467257
DEF | Battlefield Management System (BMS) | 75 | 70 | 2006-2012 | 6 | 52.5 | 8.75 | 52.5 | 47491242.17 | Military | 8678.1351 | 23.41% | 17.5538 |  | suspended | suspended | [6 empty] | https://rijksictdashboard.nl/ict-activiteiten/a5b6b639-f62f-4cc9-8bed-14a8161db378
DEF | Datacommunicatie Mobiel Optreden (DCMO) | 37.5 | 70 | 2008-2012 | 4 | 26.25 | 6.5625 | 26.25 | 23745621.08 | Military | 5415.0589 | 20.63% | 7.7374 |  | unknown | unknown
DEF | Defensiepas/ Basisvoorziening Betrouwbare Communicatie (BBC) | 20.9 | 100 | 2004-2008 | 4 | 20.9 | 5.225 | 20.9 | 18906037.36 | Military | 4637.1842 | 19.72% | 4.1224 |  | completed | completed | [6 empty] | T1
|  | 5841.17 |  |  |  | 4175.0275 | 839.2466 | [5 empty] | 2362.495 |  |  |  | 18 | 18 | 18 | 19 | 19 | 16
EXPLANATION OF THE CALCULATION
see separate sheet | [20 empty] | Projects with M&T | 18
[21 empty] | Estimate Cost | 1827.8
| investigate what became of the projects mentioned in the Excel, | [19 empty] | Final coast | 1615.64
| in the case of failure/overrun assess whether the predictions (400-2000 million exposure) materialized | [13 empty] | active | 16
[15 empty] | cancelled | 1
[15 empty] | complete | 1
Cost groups - Current Status Counts
| COUNTA of Combined status | Combined status
| Grouped Planned Cost (mln EUR) | cancelled | completed | suspended | unknown
| 0 - 20 | 4 | 3 |  | 2
| 20 - 40 | 10 | 9 |  | 5
| 40 - 60 | 3 | 6 |  | 2
| 60 - 80 |  | 4 | 1 | 1
| 80 - 100 | 1 | 3 |  | 2
| 100 - 120 | 1 | 1
| 120 - 140 | 1 | 2
| 140 - 160 | 1 | 2
| 160 - 180 |  | 2
| 180 - 200 |  |  | 1 | 1
| > 200 |  | 5
| total by status | 21 | 37 | 2 | 13
DATA on projects with known latest cost (A174)
| Total predicted loss | Total known loss
| 834.4792 | 131.8
Total Overrun (excluding negative overruns, i.e. underruns)
434.91
time / cost overrun
Don't move!
line y=x is manually added
Filter: has Actual duration data
Min | Description | Planned Cost (mln EUR) | % IT | time period | Planned Duration (year) | IT EUR(mln) | IT/year | software EUR(mln) | dollars 99 | Benchmark | size (FP) | probability of failure | failure(mln EUR) |  | Current status | Combined status | Online date | Actual Duration (year) | Time Overrun (years) | Lastest cost | Cost Overrun (mln EUR) | Overrun(M&T) | info link
SZW | Killen en Migreren (UWV) | 11 | 100 | 2006-2009 | 3 | 11 | 3.6667 | 11 | 9950545.978 | MIS | 4811.3414 | 31.89% | 3.5083 |  | active | completed | 31-12-2011 | 5 | 2 | 111 | 100 | M&T | https://rijksictdashboard.nl/ict-activiteiten/715d29e9-380c-430a-92b5-ef9848b7fde9
BZK | Nationaal Schengen Informatiesysteem (NSIS-II)(renamed to NL-SIS-II (Nederlands Schengen Informatiesysteem)) | 17.5 | 100 | 2005-2008 | 3 | 17.5 | 5.8333 | 17.5 | 15830414.06 | MIS | 6621.3097 | 35.15% | 6.1508 |  | active | completed | 31-12-2013 | 8 | 5 | 22.8 | 5.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/1c2220dc-caea-45a3-8004-bfc173e3947f
VWS | Programma Stroomlijning indicatieprocessen in Zorg en Sociale Zekerheid(renamed to Programma Stroomlijning Indicatieprocessen (STIP)) | 25 | 80 | 2006-2011 | 5 | 20 | 4 | 20 | 18091901.78 | MIS | 7258.1636 | 36.05% | 9.0135 |  | completed | completed | 2009-01-09 | 3 | -2 | 4.72 | -20.28 |  | https://rijksictdashboard.nl/ict-activiteiten/baa114a3-4559-407f-ba15-c4a30c800442
JUS | Programma NoorderWint | 35 | 95 | 2005-2010 | 5 | 33.25 | 6.65 | 33.25 | 30077786.71 | MIS | 10295.5924 | 39.31% | 13.7577 |  | active | completed | 31-01-2011 | 6 | 1 | 55 | 20 | M&T | https://rijksictdashboard.nl/ict-activiteiten/6a20e4b6-c125-48c5-b5c7-3fa1f7356ea6
DEF | Herinrichting Personele Functiegebied | 36.1 | 22 | 2004-2009 | 5 | 7.942 | 1.5884 | 7.942 | 7184294.196 | MIS | 3845.7217 | 29.57% | 10.6745 |  | active | completed | 31-12-2011 | 7 | 2 | 37.9 | 1.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/c109adb4-3a3a-4df4-ba0f-5849ccc8a43d
DEF | PALS | 36.6 | 82 | 2006-2011 | 5 | 30.012 | 6.0024 | 30.012 | 27148707.81 | MIS | 9595.1017 | 38.68% | 14.1577 |  | active | completed | 31-12-2015 | 9 | 4 | 29 | -7.6 | T | https://rijksictdashboard.nl/ict-activiteiten/2e6d6fb1-50c7-47bc-8d56-d5e0fe5d95d1
FIN | Vooringevulde aangifte (VIA) | 45 | 55 | 2006-2008 | 2 | 24.75 | 12.375 | 24.75 | 22388728.45 | MIS | 8403.7464 | 37.46% | 16.8576 |  | active | completed | 2012-05-01 | 6 | 4 | 53.26 | 8.26 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f5a8b162-363e-480a-8d0f-e21c0eedae65
FIN | Basisregistraties | 46 | 93 | 2007-2010 | 3 | 42.78 | 14.26 | 42.78 | 38698577.9 | MIS | 12243.9875 | 40.77% | 18.7531 |  | active | completed | 31-12-2015 | 8 | 5 | 42.7 | -3.3 | T | https://rijksictdashboard.nl/ict-activiteiten/2de4f98a-9342-40b8-b5c4-c76d6269cc92
FIN | eCustoms | 47.6 | 55 | 2005-2012 | 7 | 26.18 | 3.74 | 26.18 | 23682299.43 | MIS | 8734.7353 | 37.82% | 18.0036 |  | active | completed | 31-12-2010 | 5 | -2 | 65.28 | 17.68 | M | https://rijksictdashboard.nl/ict-activiteiten/ce9d570c-f711-4bb1-953b-01a62f444c03
JUS | Vernieuwing informatievoorziening DJI | 50 | 100 | 2002-2012 | 10 | 50 | 5 | 50 | 45229754.45 | MIS | 13630.2039 | 41.61% | 20.8044 |  | active | completed | 31-12-2013 | 11 | 1 | 4.2 | -45.8 | T | https://rijksictdashboard.nl/ict-activiteiten/7322396e-dea8-4d38-9273-c197eb79180c
VenW | Modernisering Objecten Bediening Zeeland | 62 | 80 | 2004-2010 | 6 | 49.6 | 8.2667 | 49.6 | 44867916.41 | MIS | 13555.1186 | 41.57% | 25.7713 |  | active | completed | 31-12-2018 | 14 | 8 | 62.93 | 0.93 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f50705ba-ec4e-4893-ac46-ff5ed127e922
FIN | Herinrichting invorderingsproces(renamed to ETM) | 78 | 100 | 2005-2008 | 3 | 78 | 26 | 78 | 70558416.94 | MIS | 18506.3208 | 43.71% | 34.0967 |  | active | completed | 31-12-2010 | 5 | 2 | 175.3 | 97.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/44407368-191b-4ae7-b727-7eab039661b7
JUS | Vernieuwing IND (renamed to INDIGO) | 80 | 50 | 2006-2010 | 4 | 40 | 10 | 40 | 36183803.56 | MIS | 11691.0724 | 40.39% | 32.312 |  | active | completed | 31-12-2013 | 7 | 3 | 98 | 18 | M&T | https://rijksictdashboard.nl/ict-activiteiten/7bec8d3e-7062-41fb-a2e3-bdc1edf7c518
JUS | GPS | 90 | 25 | 2000-2010 | 10 | 22.5 | 2.25 | 22.5 | 20353389.5 | MIS | 7870.5651 | 36.84% | 33.1548 |  | active | completed | 31-12-2011 | 11 | 1 | 99.4 | 9.4 | M&T | https://rijksictdashboard.nl/ict-activiteiten/132afe97-ad4f-49fc-b789-f3010c85c893
SZW | SVB Tien (SVB) | 92 | 30 | 2006-2010 | 4 | 27.6 | 6.9 | 27.6 | 24966824.45 | MIS | 9057.8663 | 38.16% | 35.1057 |  | cancelled | cancelled | 2014-02-09 | 8 | 4 | 121.8 | 29.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/09b1ce9a-294f-48db-96b9-bf5cb79305cc
DEF | SPEER | 150 | 33 | till 2013 | 4.7897 | 49.5 | 10.3348 | 49.5 | 44777456.9 | MIS | 13536.3178 | 41.56% | 62.3341 |  | active | completed | 31-12-2015 | 6.7897 | 2 | 276.44 | 126.44 | M&T | https://rijksictdashboard.nl/ict-activiteiten/85e1279b-0c14-45f1-b144-3144cf75c544
FIN | Toeslagen | 275 | 81 | 2005-2008 | 3 | 222.75 | 74.25 | 222.75 | 201498556.1 | MIS | 38083.329 | 46.83% | 128.796 |  | active | completed | 23-12-2011 | 6 | 3 | 240 | -35 | T | https://rijksictdashboard.nl/ict-activiteiten/e65803ab-6288-40f4-95bb-7b4ba269a327
BZK | P-direkt | 700 | 42 | 2004-2018 | 12 | 294 | 24.5 | 294 | 265950956.1 | MIS | 46092.1361 | 47.27% | 330.8619 |  | active | completed | 31-12-2010 | 4 | -8 | 115.91 | -584.09 |  | https://rijksictdashboard.nl/ict-activiteiten/e404d751-2023-4ddb-86c1-5469bc63317f
434.91
Filter: has Latest cost data | [12 empty] | 834.4792 | [7 empty] | -301.16
Min | Description | Planned Cost (mln EUR) | % IT | time period | Planned Duration (year) | IT EUR(mln) | IT/year | software EUR(mln) | dollars 99 | Benchmark | size (FP) | probability of failure | failure(mln EUR) |  | Current status | Combined status | Online date | Actual Duration (year) | Time Overrun (years) | Lastest cost | Cost Overrun (mln EUR) | Overrun(M&T) | info link
BZK | P-direkt | 700 | 42 | 2004-2018 | 12 | 294 | 24.5 | 294 | 265950956.1 | MIS | 46092.1361 | 47.27% | 330.8619 |  | active | completed | 31-12-2010 | 4 | -8 | 115.91 | -584.09 |  | https://rijksictdashboard.nl/ict-activiteiten/e404d751-2023-4ddb-86c1-5469bc63317f
FIN | Toeslagen | 275 | 81 | 2005-2008 | 3 | 222.75 | 74.25 | 222.75 | 201498556.1 | MIS | 38083.329 | 46.83% | 128.796 |  | active | completed | 23-12-2011 | 6 | 3 | 240 | -35 | T | https://rijksictdashboard.nl/ict-activiteiten/e65803ab-6288-40f4-95bb-7b4ba269a327
FIN | Herinrichting invorderingsproces(renamed to ETM) | 78 | 100 | 2005-2008 | 3 | 78 | 26 | 78 | 70558416.94 | MIS | 18506.3208 | 43.71% | 34.0967 |  | active | completed | 31-12-2010 | 5 | 2 | 175.3 | 97.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/44407368-191b-4ae7-b727-7eab039661b7
JUS | Vernieuwing informatievoorziening DJI | 50 | 100 | 2002-2012 | 10 | 50 | 5 | 50 | 45229754.45 | MIS | 13630.2039 | 41.61% | 20.8044 |  | active | completed | 31-12-2013 | 11 | 1 | 4.2 | -45.8 | T | https://rijksictdashboard.nl/ict-activiteiten/7322396e-dea8-4d38-9273-c197eb79180c
VenW | Modernisering Objecten Bediening Zeeland | 62 | 80 | 2004-2010 | 6 | 49.6 | 8.2667 | 49.6 | 44867916.41 | MIS | 13555.1186 | 41.57% | 25.7713 |  | active | completed | 31-12-2018 | 14 | 8 | 62.93 | 0.93 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f50705ba-ec4e-4893-ac46-ff5ed127e922
DEF | SPEER | 150 | 33 | till 2013 | 4.7897 | 49.5 | 10.3348 | 49.5 | 44777456.9 | MIS | 13536.3178 | 41.56% | 62.3341 |  | active | completed | 31-12-2015 | 6.7897 | 2 | 276.44 | 126.44 | M&T | https://rijksictdashboard.nl/ict-activiteiten/85e1279b-0c14-45f1-b144-3144cf75c544
FIN | Basisregistraties | 46 | 93 | 2007-2010 | 3 | 42.78 | 14.26 | 42.78 | 38698577.9 | MIS | 12243.9875 | 40.77% | 18.7531 |  | active | completed | 31-12-2015 | 8 | 5 | 42.7 | -3.3 | T | https://rijksictdashboard.nl/ict-activiteiten/2de4f98a-9342-40b8-b5c4-c76d6269cc92
BZ | Werken in de Toekomst (WIT) | 50 | 85 | 2008-2001 | 7 | 42.5 | 6.0714 | 42.5 | 38445291.28 | MIS | 12188.8175 | 40.73% | 20.3655 |  | cancelled | cancelled |  |  |  | 10 | -40 |  | T1
JUS | Vernieuwing IND (renamed to INDIGO) | 80 | 50 | 2006-2010 | 4 | 40 | 10 | 40 | 36183803.56 | MIS | 11691.0724 | 40.39% | 32.312 |  | active | completed | 31-12-2013 | 7 | 3 | 98 | 18 | M&T | https://rijksictdashboard.nl/ict-activiteiten/7bec8d3e-7062-41fb-a2e3-bdc1edf7c518
JUS | Programma NoorderWint | 35 | 95 | 2005-2010 | 5 | 33.25 | 6.65 | 33.25 | 30077786.71 | MIS | 10295.5924 | 39.31% | 13.7577 |  | active | completed | 31-01-2011 | 6 | 1 | 55 | 20 | M&T | https://rijksictdashboard.nl/ict-activiteiten/6a20e4b6-c125-48c5-b5c7-3fa1f7356ea6
DEF | PALS | 36.6 | 82 | 2006-2011 | 5 | 30.012 | 6.0024 | 30.012 | 27148707.81 | MIS | 9595.1017 | 38.68% | 14.1577 |  | active | completed | 31-12-2015 | 9 | 4 | 29 | -7.6 | T | https://rijksictdashboard.nl/ict-activiteiten/2e6d6fb1-50c7-47bc-8d56-d5e0fe5d95d1 | FALSE
SZW | SVB Tien (SVB) | 92 | 30 | 2006-2010 | 4 | 27.6 | 6.9 | 27.6 | 24966824.45 | MIS | 9057.8663 | 38.16% | 35.1057 |  | cancelled | cancelled | 2014-02-09 | 8 | 4 | 121.8 | 29.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/09b1ce9a-294f-48db-96b9-bf5cb79305cc
FIN | eCustoms | 47.6 | 55 | 2005-2012 | 7 | 26.18 | 3.74 | 26.18 | 23682299.43 | MIS | 8734.7353 | 37.82% | 18.0036 |  | active | completed | 31-12-2010 | 5 | -2 | 65.28 | 17.68 | M | https://rijksictdashboard.nl/ict-activiteiten/ce9d570c-f711-4bb1-953b-01a62f444c03
FIN | Vooringevulde aangifte (VIA) | 45 | 55 | 2006-2008 | 2 | 24.75 | 12.375 | 24.75 | 22388728.45 | MIS | 8403.7464 | 37.46% | 16.8576 |  | active | completed | 2012-05-01 | 6 | 4 | 53.26 | 8.26 | M&T | https://rijksictdashboard.nl/ict-activiteiten/f5a8b162-363e-480a-8d0f-e21c0eedae65
JUS | GPS | 90 | 25 | 2000-2010 | 10 | 22.5 | 2.25 | 22.5 | 20353389.5 | MIS | 7870.5651 | 36.84% | 33.1548 |  | active | completed | 31-12-2011 | 11 | 1 | 99.4 | 9.4 | M&T | https://rijksictdashboard.nl/ict-activiteiten/132afe97-ad4f-49fc-b789-f3010c85c893
VWS | Programma Stroomlijning indicatieprocessen in Zorg en Sociale Zekerheid(renamed to Programma Stroomlijning Indicatieprocessen (STIP)) | 25 | 80 | 2006-2011 | 5 | 20 | 4 | 20 | 18091901.78 | MIS | 7258.1636 | 36.05% | 9.0135 |  | completed | completed | 2009-01-09 | 3 | -2 | 4.72 | -20.28 |  | https://rijksictdashboard.nl/ict-activiteiten/baa114a3-4559-407f-ba15-c4a30c800442
BZK | Nationaal Schengen Informatiesysteem (NSIS-II)(renamed to NL-SIS-II (Nederlands Schengen Informatiesysteem)) | 17.5 | 100 | 2005-2008 | 3 | 17.5 | 5.8333 | 17.5 | 15830414.06 | MIS | 6621.3097 | 35.15% | 6.1508 |  | active | completed | 31-12-2013 | 8 | 5 | 22.8 | 5.3 | M&T | https://rijksictdashboard.nl/ict-activiteiten/1c2220dc-caea-45a3-8004-bfc173e3947f
SZW | Killen en Migreren (UWV) | 11 | 100 | 2006-2009 | 3 | 11 | 3.6667 | 11 | 9950545.978 | MIS | 4811.3414 | 31.89% | 3.5083 |  | active | completed | 31-12-2011 | 5 | 2 | 111 | 100 | M&T | https://rijksictdashboard.nl/ict-activiteiten/715d29e9-380c-430a-92b5-ef9848b7fde9
DEF | Herinrichting Personele Functiegebied | 36.1 | 22 | 2004-2009 | 5 | 7.942 | 1.5884 | 7.942 | 7184294.196 | MIS | 3845.7217 | 29.57% | 10.6745 |  | active | completed | 31-12-2011 | 7 | 2 | 37.9 | 1.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/c109adb4-3a3a-4df4-ba0f-5849ccc8a43d
Filter: (Currrent status = suspended or cancelled) or (Overrun cost > 0) | [19 empty] | 131.8
Min | Description | Planned Cost (mln EUR) | % IT | time period | Planned Duration (year) | IT EUR(mln) | IT/year | software EUR(mln) | dollars 99 | Benchmark | size (FP) | probability of failure | failure(mln EUR) |  | Current status | Combined status | Online date | Actual Duration (year) | Time Overrun (years) | Lastest cost | Cost Overrun (mln EUR) | Overrun(M&T) | info link
FIN | Complexiteitsreductie | 200 | 90 | 2006-2015 | 9 | 180 | 20 | 180 | 162827116 | MIS | 32891.8814 | 46.4% | 92.8061 |  | suspended | suspended | [6 empty] | T1
VenW | VTI, Programma Vaste Telecom Infra | 117 | 100 | 2006-2011 | 5 | 117 | 23.4 | 117 | 105837625.4 | MIS | 24458.1424 | 45.22% | 52.9132 |  | cancelled | cancelled | [6 empty] | T1
VenW | InfoPlus | 143 | 80 | Oct 2000 - Oct 2009 | 9 | 114.4 | 12.7111 | 114.4 | 103485678.2 | MIS | 24083.0412 | 45.15% | 64.5667 |  | cancelled | cancelled | [6 empty] | T1
SZW | wet Werk en Inkomen naar Arbeidsvermogen (UWV) | 127 | 60 | Oct 2005 till medio 2008 | 2.8 | 76.2 | 27.2143 | 76.2 | 68930145.78 | MIS | 18211.5432 | 43.61% | 55.3905 |  | cancelled | cancelled | [6 empty] | T1
SZW | Walvis/SUB SZW Digitaal Klantdossier (CWI) | 59.1 | 80 | 2005-2008 | 3 | 47.28 | 15.76 | 47.28 | 42769255.8 | MIS | 13115.8254 | 41.31% | 24.4159 |  | cancelled | cancelled | [6 empty] | T1
BZ | Werken in de Toekomst (WIT) | 50 | 85 | 2008-2001 | 7 | 42.5 | 6.0714 | 42.5 | 38445291.28 | MIS | 12188.8175 | 40.73% | 20.3655 |  | cancelled | cancelled |  |  |  | 10 | -40 |  | T1
OCW | Wijziging studiefinancieringssytemen IBGroep | 54.2 | 72 | 2006-2011 | 5 | 39.024 | 7.8048 | 39.024 | 35300918.75 | MIS | 11494.1334 | 40.25% | 21.815 |  | cancelled | cancelled | [6 empty] | T1
SZW | USMF (UWV) | 31.1 | 100 | 2002-2007 | 5 | 31.1 | 6.22 | 31.1 | 28132907.27 | MIS | 9832.9911 | 38.9% | 12.0984 |  | cancelled | cancelled | [6 empty] | T1
VenW | Herman | 30.5 | 95 | Q3-2006 t/m Q1-2009 | 2.5 | 28.975 | 11.59 | 28.975 | 26210642.7 | MIS | 9365.8437 | 38.46% | 11.7314 |  | cancelled | cancelled | [6 empty] | T1
SZW | SVB Tien (SVB) | 92 | 30 | 2006-2010 | 4 | 27.6 | 6.9 | 27.6 | 24966824.45 | MIS | 9057.8663 | 38.16% | 35.1057 |  | cancelled | cancelled | 2014-02-09 | 8 | 4 | 121.8 | 29.8 | M&T | https://rijksictdashboard.nl/ict-activiteiten/09b1ce9a-294f-48db-96b9-bf5cb79305cc
VenW | VenW Beschikbaarheid In Zicht (BIZ) 25 100 | 25 | 100 | NA | 2.5 | 25 | 10 | 25 | 22614877.22 | MIS | 8462.0337 | 37.53% | 9.3816 |  | cancelled | cancelled | [6 empty] | T1
VenW | VIP21 | 21.4 | 100 | 2005-2008 | 3 | 21.4 | 7.1333 | 21.4 | 19358334.9 | MIS | 7603.8734 | 36.51% | 7.8124 |  | cancelled | cancelled | [6 empty] | T1
VenW | Walradar Noordzeekanaal | 26.2 | 80 | 2005-2009 | 4 | 20.96 | 5.24 | 20.96 | 18960313.06 | MIS | 7496.0044 | 36.37% | 9.5285 |  | cancelled | cancelled | [6 empty] | T1
BZK | Basisvoorziening Handhaving (BVH) | 15 | 100 | Mar 2007 - Sep 2009 | 2.6 | 15 | 5.7692 | 15 | 13568926.33 | MIS | 5955.2848 | 34.08% | 5.1122 |  | cancelled | cancelled | [6 empty] | T1
BZK | HAVANK | 30 | 50 | t/m 2009 | 3.3831 | 15 | 4.4338 | 15 | 13568926.33 | MIS | 5955.2848 | 34.08% | 10.2243 |  | cancelled | cancelled | [6 empty] | T1
VenW | ASTRIS | 20.5 | 70 | 2007-2011 | 4 | 14.35 | 3.5875 | 14.35 | 12980939.53 | MIS | 5776.5832 | 33.77% | 6.9232 |  | cancelled | cancelled | [6 empty] | T1
VenW | Trots | 18.7 | 70 | 2004-2009 | 5 | 13.09 | 2.618 | 13.09 | 11841149.71 | MIS | 5422.782 | 33.13% | 6.1945 |  | cancelled | cancelled | [6 empty] | T1
SZW | Digitaal Verzekeringsbericht (UWV) | 20.6 | 60 | Sept 2006 - Q1 2009 | 2.5 | 12.36 | 4.944 | 12.36 | 11180795.3 | MIS | 5212.9443 | 32.72% | 6.7404 |  | cancelled | cancelled | [6 empty] | T1
VenW | DONNA | 20 | 60 | till medio 2009 | 3.1703 | 12 | 3.7851 | 12 | 10855141.07 | MIS | 5108.0429 | 32.51% | 6.5022 |  | cancelled | cancelled | [6 empty] | T1
BZK | Basisvoorziening Opsporing (BVO) | 12 | 85 | Jan 2007 - medio 2008 | 1.5 | 10.2 | 6.8 | 10.2 | 9226869.907 | MIS | 4567.8702 | 31.36% | 3.7627 |  | cancelled | cancelled | [6 empty] | T1
EZ | Nieuw handelsregister | 20 | 50 | 2002-2010 | 8 | 10 | 1.25 | 10 | 9045950.889 | MIS | 4506.0826 | 31.21% | 6.2429 |  | cancelled | cancelled | [6 empty] | T1
BZK | Basisvoorziening Capaciteitsmanagement (BVCM) | 19 | 51 | Mar 2007 - Jul 2009 | 2.5 | 9.69 | 3.876 | 9.69 | 8765526.412 | MIS | 4409.5431 | 30.99% | 5.888 |  | cancelled | cancelled | [6 empty] | T1
DEF | Battlefield Management System (BMS) | 75 | 70 | 2006-2012 | 6 | 52.5 | 8.75 | 52.5 | 47491242.17 | Military | 8678.1351 | 23.41% | 17.5538 |  | suspended | suspended | [6 empty] | https://rijksictdashboard.nl/ict-activiteiten/a5b6b639-f62f-4cc9-8bed-14a8161db378

## Explanation
The portfolio used is located at:
http://www.minbzk.nl/aspx/download.aspx?file=/contents/pages/90083/bijlageinventarisatiegroteict-projecten.pdf
In case of an a-b notation, the average percentage/costs are taken (this occurred 10 times). There is one project with an >a notation, in this case a is taken.
The benchmark used is described in the following book:
Capers Jones, Software Assessments, Benchmarks, and Best practices, Addison-Wesley, 2000, ISBN 0-201-48542-7
Tabel 1.3 (p18) lists the number of projects used. For the interesting categories these are:
size (FP) | MIS | Outsourced | Military
1 | 50 | 50 | 20
10 | 225 | 135 | 50
100 | 1600 | 550 | 150
1000 | 1250 | 475 | 125
10000 | 175 | 90 | 60
100000 | 0 | 0 | 2
Total | 3300 | 1300 | 407
Table 7.7(p191) describes the connection between function points and costs for MIS projects. From these, a formula was derived:
size (FP) | Avg costs/FP |  | Avg costs | fitted FP (R^2=1.000 with log-log transformation)
100 | 352.46 |  | 35246 | 99.2702
1000 | 1035.46 |  | 1035460 | 1014.9012
10000 | 2851.9 |  | 28519000 | 9925.6005
Table 8.8 (p274) describes the connection between function points and costs for outsourced projects. From these, a formula was derived:
size (FP) | Avg costs/FP |  | Avg costs | fitted FP (R^2=1.000 with log-log transformation)
100 | 459.21 |  | 45921 | 101.087
1000 | 1104.31 |  | 1104310 | 978.899
10000 | 2904.62 |  | 29046200 | 10105.7106
Table 11.7 (p498) describes the connection between function points and costs for military projects. From these, a formula was derived:
size (FP) | Avg costs/FP |  | Avg costs | fitted FP (R^2=1.000 with log-log transformation)
1000 | 1949.84 |  | 1949840 | 988.4684
10000 | 6055.47 |  | 60554700 | 10238.4168
100000 | 16950.45 |  | 1695045000 | 98811.1356
Table 7.8(p192), 8.8(p275) and 11.8(p499) describe the relation between function points and canceled projects
size(FP) | MIS | Outsourced | Military
1 | 1% | 1% | 0.5513%
10 | 1.372% | 0.5149% | 1.603%
100 | 5.091% | 2.384% | 6%
1000 | 16.89% | 9.923% | 10%
10000 | 39.05% | 27.01% | 25%
100000 | 47.98% | 33% | 33.2%
The fit used is already entered in the cells that are equal to the original table.
This method is described in:
C. Verhoef, Quantitative IT portfolio management, Science of Computer Programming, Volume 45, Issue 1, October 2002, Pages 1-96.
http://www.cs.vu.nl/~x/ipm/ipm.pdf
The benchmark used describes the situation in 1999 and uses costs in dollars.
Current euros have to be translated to this unit
On the site of DNB the following information is listed:
via | http://www.statistics.dnb.nl/index.cgi?lang=nl&todo=Koersen
1999
Amerikaanse dollar * | 1.0658
* Source: ECB
Thereby, the conversion rate used is 1.0658
Next to that, inflation is corrected for. From CBS Statline, table Historische Inflatie:
via | http://statline.cbs.nl/
Onderwerpen | Inflatie, afgeleid |  | Calculated index
Perioden | % |  | 1
1999 | 1.7 |  | 1.017
2000 | 2.2 |  | 1.0394
2001 | 3.6 |  | 1.0768
2002 | 3.4 |  | 1.1134
2003 | 1.9 |  | 1.1346
2004 | 0.9 |  | 1.1448
2005 | 1.4 |  | 1.1608
2006 | 1.5 |  | 1.1782
Inflatie, afgeleid
De reeks Inflatiecijfers, afgeleid is gelijk aan de gewone reeks,
exclusief het effect van veranderingen in de tarieven van
productgebonden belastingen (bijvoorbeeld BTW en accijns op
alcohol en tabak) en subsidies.
The correction for inflation used is 1.178206706 . The inflation correction has been adjusted for the effect of taxation.

## Scenario Summary
Scenario Summary
|  | Current Values: | low | normal | high
|  |  | Created by pkampst on 7/10/2008 | Created by pkampst on 7/10/2008 | Created by pkampst on 7/10/2008
Changing Cells:
| largest_project | 50 | 20 | 50 | 100
| failed_budget | 75 | 20 | 75 | 100
Result Cells:
| total_loss | 1637.8309 | 377.9984 | 1637.8309 | 2362.495
| total_loss_percent | 37.39% | 32.36% | 37.39% | 40.45%
| risk_excess_percent | 19.51% | 14.48% | 19.51% | 22.57%
| normal_loss | 780.3149 | 208.084 | 780.3149 | 1040.4198
| risk_excess | 854.714 | 169.1673 | 854.714 | 1318.3392
Notes: Current Values column represents values of changing cells at
time Scenario Summary Report was created. Changing cells for each
scenario are highlighted in gray.